## Overview
Broad Overview of Marketing and Sales - 5 Months
February
Work with GM on story of hotel and introducing key team members and partners
Establish sales plan with quarterly objectives
Establish Annual Sales and Event calendar
Begin developing grand opening plan
Work with City to iron out the event booking system
March
Complete website
Complete all handout and packaged materials
Sales visits and sales calls
Ensure hotel is signed up for all relevant listings and memberships
Developing Social Media plan
Active Social Media
April
Sales visits and calls
Planning for grand opening
Setting up all reservations systems, OTA, channel management, etc.
Active Social Media
Grand Opening planning
Develop open house schedule
Work with local wine, local business and art for receptions
May
Sales visits and calls
Plan for training staff on sales
Grand Opening planning
PR - press releases, media outreach
Active on Social Media
Quality control on sales
June
Many details related to marketing, PR and grand opening (see sheets)
Press releases and media outreach
Friends and Family early stays
Engagement with staff on telling the story of the hotel, restaurant and area

## 1 Month Out
Pre-Opening Sales - 1 Month
Task | Department | Comments | Completion Date
Ownership and Management Company "Thank You" notes to opening team
Confirm messages on all reservations
Review reservations including influencers
Visit a travel agent and review information, accessibility and ability to be booked
Make direct sales calls to all businesses in Polk Co. targeted businesses in Salem, Corvallis, etc.
QC-Sales/Res
2 WEEKS OUT
Work on the story with staff/ Description- Hotel/Res/Sales staffs- Debrief hotel and restaurant staffs on how each sells and describes their business and the others business to each other
Restaurant / Hotel GM schedule meeting on collaboration
Test meal schedule - Staff should test meals
Review reservations coverage- next 2 weeks and weekends
Establish Weekly Sales Reports
Lobby Signs - think about posters or signage for walk-ins
Orientat Front Desk to Open House Program
Develop plan for the 1st guest (name a room after them, etc)
1 WEEK OUT
Quality controls sales and reservations
Work nearby hotels for referrals / overflow
Develop show room program
Restaurant orientation for hotel bell, door, desk and reservation staff and tour
Hotel tour for restaurant staff
Res Blitz all relevant Salem and other hotels for overflow
Consider extra person-outside labor to help covers sales phones (first 4 weeks)
Sales traning staff - take reservations answer sales calls
GRAND OPENING
Review pre-opening activities and checklist
Lobby sign in soft openings
Desk ask for guest to ID ops problems- reward for each idea
Host open house/tours for key leads
Travel Agent Free Spree (TFS)
Friends and Family Rate- promote in local market, WORD, etc. for all staff's friends & family
Implement Sales Month-End Reports/ National Tracking and AMEX Reports
Review booking pace and actual sales
Update on any appropriate press materials
Continuing to maintain monthly calendar of events
Continue working with hotel DOS and GM on the development of new ideas
Set up media reservation with hotel
Update on Opening Party
Update on ribbon cutting
Update on local pitches
Update on press tip
Set up media reservation with hotel
Detail first 90 days
VIP/ Grand Opening events
Mail package information press release
Conduct photo shoot
Radio blitz
Get photo transparencies; organize, file and order

## 2 Month
Pre-Opening Checklist-Month 2
Task | Department | Comments | Completion Date
MARKETING
Review Sales Basics
Identify cab promo
Maintain sales visits and calls - hard hat tours, etc.
Begin fine tuning open-house schedule
Review Pre-Open Budget and Ops Budget
Review all hotel fact sheets
Grand Opening Checklist
Visit a travel agent and review information accessibility and ability to be booked
Make sure all construction, design, architect, local, legal and back staffs are properly "thanked"- (this could be test meal, comp rooms, their own open house, etc)
Letter to Investors with update and invite to grand openng
Corporate website -verify photos-all links
SALES
Preview on-site tours with key accounts
SOCIAL MEDIA
2-3 social media promotions/contests per year. Will work with client to create creative contest of their choice
Begin establishing presence across other social outlets- ex. TripAdvisor, YouTube, Yelp, Google Places, Foursquare, etc
Email-marketing Campaigns
Determine if intern is appropriate - local colleges. Business/ H& R Departments
Review Booking pace and actual sales
Review Sales Team performance based upon goals outlined
Revisit Sales Team performance goals based upon operating budget
PUBLIC RELATIONS
Lead conversation with staff and partners about publicity ideas
Continuing to maintain monthly calendar of events
Set up media reservation with hotel
Update on opening Party
Update on ribbon cutting
Update on local pitches
Update on press trip
Update on Agent FAM promo
REVENUE
Review opening inventory with GM to determine number of available room at opening that will be released by construction
Distribute Updated Sell Strategy to GM, Sales team, Reservations team
Grand Opening Party - discuss allocation of rooms with GM, DOS

## 3 Month
Pre-Opening Checklist-Month 3
Task | Department | Comments | Completion Date
MARKETING
Develop direct sales action plan with restaurant
Review Pre-Opening budget and Ops budget
Review grand opening and open house plans with key team members
SALES
Develop manuals (trace system/ database, letters, procedures, meeting space, reports)
Finalize presentation binder
Identify local accounts/ coordinate Direct sales calls on key local accounts
Detail sales roles of staff
Research sales opportunities including RFPs and non-traditional approaches
Create opening promo to be communicated with the key consortia partners
PUBLIC RELATIONS
GENERAL PR
Update on any appropriate press materials
Continuing to maintain monthly calendar of events- show through the first 12 months of operations
Set up media reservation with hotel
Update on Opening Party
Update on Local Pitches
REVENUE
Order Star, Hotelogence and Rate View reports for the hotel
Enter committed reservations, groups, and initiate inventory controls in CRS, PMS based on Sell Strategy Sheet
Complete 30 60 90 Forecast
Begin Group and Transient Pace Report
Meet with Controller to discuss operations of direct billing, advance deposits, no shows, and refunds for the aforementioned
GIVE Tours of Hotel to: local business, Travel Agents, comp set
DISTRIBUTION
Add hotel to all directories
Make sure hotel set up with all associations, etc.
Send hotel rep. to communty meetings as needed
Website translation consideration
Online marketng campaigns
GDS (headlines)
Third Party E-Channels (Destinations pages, Sort order)
Check hotel address and local listings
Yellow Pages (www.bigyellow.com)
MapQuest accuracy
Email marketing for grand opening
Complete masthead and footer for email campaign template
Complete email marketing rate loading

## 4 Month
Pre-Opening Checklist-Month 4
Task | Department | Comments | Completion Date
MARKETING
Review Pre-Opening Budget/ Ops Budget
Develop local and regional partner list and load into communications sytes
Get all sales 'Stories" in order
Finalize opening "Introductory Rate" or bounce back is appropriate
Brand Signage
Free Spree for influences plan firmed up
Establish and implement sales calls and visits and capaigns
Review on-hold message for hotel sales and reservations
Detail for Packages and promos should be final-Pet Friendly activities/ program defined
Joint meetings with restaurant and hotel management team
Restaurant Theme info for staff to be able to talk about
Initiate Guest Loyalty Checklist
Develop iteneraries for guests and market them
PR- First guest plan
Confirm public bathroom, elevator, and in room restaurant signage
Review Sales Basics
SALES
Review weekly Sales Schedules / Calendar
Start 3 block sales call program
Develop pricing structure for wholesale / Corporate Accounts
Develop National Sales Target Account List
Staff should be calling other hotels to get a sense of good and bad examples of sales
Sales Best Practices
Plan and confirm sales training for staff
Review rough draft of Annual Business Plan with VP, Sales
Contract and build listings on OTA Sites
Complete OTA checklist
Create strategy to invite key Travel Managers/ Meeting Planners to experience the hotel during the first 90- days of opening
PUBLIC RELATIONS
GENERAL PR
Continue to maintain calendar of events
Work with hotel to create holiday package ideas
Identify local pitches regarding wellness, pets, lifestyle, charities, etc.
Update opening party
Press Trip
REVENUE
Revenue Best Practices
Create Bounce back program for the first 6 months (incentive, etc.-may need to allow time for printing, etc)
Develop Hot Facts or hotel Sell Sheet for effective selling
MARKETING
Confirm opening day (Advise Marketing and Technology related departments
Identify when PMS and Sales technology will be available for training.
Create signature retail item
Advise Mobil/ AAA of opening day
Wall chart shoeing first 6 months goals and progress
Review Pre-Opening Budget
Exterior Promotion Activity- Banner, Mannequins, etc
Confirm Opening Party Date (Inform PR)
First guest celebration
Giveaway items
SOCIAL MEDIA
Explore & research social media and online presence of competitors Establish social media outlook- what social platforms are most important and/or relevant to client?

## 5 Month
Pre-Opening Checklist-Month 5
Task | Department | Comments | Completion Date
Work with GM on story of hotel and introducing key team members and partners
Establish sales plan with quarterly objectives
Establish Annual Sales and Event calendar
Work with City to iron out the event booking system
Identify names of the suites
Uniforms
Identify talking points on dog-friendly, bike-friendly, wellness etc.
SALES
Review sales presentation binder
Identify any directories necessary
ID large local contract key accounts
Discuss market trends and impact on sales approach
Discuss sales team structure
Discuss market segmentation and strategies to build OTB's revenue prior to opening
Create Pre-opening sales booking goals
Events plan
Register Online/offline yellow/white/ MapQuest / pets.com etc.
Begin open house prospecting process
Obtain top 500 travel for the market from TravelCLICK
Conduct "Sales Basics" training
Hotel/Restaurant collaboration
PUBLIC RELATIONS
GENERAL PR
Radio Blitz coordination
Review Partnership Programs
OPENING PARTY
Follow up for opening party
Update on opening event
Finalize concept for opening invitations
Provide final draft of media relations plan to promote opening event
Finalize and have opening event invitations printed
Continue compiling invitation lists: media, VIP's and the business community for opening event
Finalize invitation list for opening event
Mail invitations date determined
Draft media alert and/ or release for opening events and publicity stunt
Start making contracts for press trip partners
Mail Press trip invitees a "save the date" letter
Create tentative press trip schedule
Mail press trip invitations (identify when)
Decide concept theme for press trip
Follow up with media that received press kit and pitch stories
Work on the development of a master list of invitees to the press trip
Draft and distribute package press release
Create insert for press kit including package descriptions
REVENUE
Tour comp set
Complete SWOT analysis
Meet comp set Reservations Managers/ Directors of Revenue; discuss local strategies, demand periods, etc.
Get updated community event calendar
Review Demand Dates
Research local area for banking, restaurants, attractions, and transportation anything guests could ask about
Setup Standard Rates (Loyalty Rate, Friends and Family, Employee Rate, Travel Agent Rate, Donation Rate, etc.)
Discuss Policies Regarding Group Block Standards
Start Group Package Development
DISTRIBUTION
Pictures- if available (if pictures are not available, indicate this to Pegasus)
Initiate Reservations
Determine room types and descriptors
Load rates (ensure inventory master, room types, SRP Groups are loaded
GDS / WH / WB rate load forms
Set order for SRP display
Set inventory rates and restrictions
Rate loads in all channels
GDS / WH / WB rate load forms and sequencing as appropriate
Load property pictures/ logos on Travelocity via Sabre Website
Fax/ Paper
Obtain Masthead
Send Masthead
Submit logins for necessary people
PMS system selected
Client Reports
Set up email for pre-opening staff